## Gantt Chart
AI-Powered E-Commerce Shopping Assistant (Gantt Chart) — Updated v5
DS440 Capstone ¦ Penn State ¦ Spring 2026
Team Members: Arjun Shokeen, Bill Erderly
Advisor: Dr. Kaamran Raahemifar
Project Goals:
1. Build a conversational AI shopping assistant using LLM + RAG
2. Implement ReAct orchestration with guardrails and tool execution
3. Deploy full-stack prototype to public cloud URL
4. Deliver final presentation and all course deliverables
Task | Lead | Duration | Start Date | Progress | End Date | Completed Date | Comments/Updates
Environment & Consolidation | Arjun |  | 2026-02-09 | Done | 2026-02-10 | 2026-02-10 | Rebuilt from scratch with Vite + Tailwind instead of CRA migration
Migrate prototype code into commerce-agent-llm/ |  | 1 | 2026-02-09 | Done | 2026-02-09 | 2026-02-10 | Standardized on Vite + React 18 + Tailwind CSS + Zustand (not CRA)
Migrate CRA → Vite + React 18 + Tailwind CSS + Zustand |  | 1 | 2026-02-09 | Modified | 2026-02-09 | 2026-02-10 | Replaced Milvus/Redis/etcd/MinIO with numpy vectors + in-memory services
Configure numpy VectorStore + OpenAI embeddings + disk cache | Bill | 2 | 2026-02-09 | Done | 2026-02-10 | 2026-02-10 | OpenAI API key configured; Milvus/Redis not needed
Configure .env (API keys, connection strings) |  | 1 | 2026-02-10 | Done | 2026-02-10 | 2026-02-10 | OpenAI key, Milvus/Redis hosts
Backend Validation & Hardening | Arjun |  | 2026-02-11 | Done | 2026-02-15 | 2026-02-11 | 17 REST + 1 WebSocket endpoint (exceeded planned 7)
Boot FastAPI; verify all endpoints respond |  | 1 | 2026-02-11 | Done | 2026-02-11 | 2026-02-12 | numpy + OpenAI embeddings with disk cache (not Milvus/pymilvus)
Generate numpy embeddings; cache to disk (VectorStore) | Bill | 2 | 2026-02-11 | Done | 2026-02-12 | 2026-02-14 | Native OpenAI function calling (not LangChain). Added 3-tier fallback
Test ReAct orchestration loop end-to-end |  | 2 | 2026-02-12 | Done | 2026-02-13 | 2026-02-15 | RRF implemented. Tokenized keyword search across all fields
Validate hybrid search (semantic + keyword / RRF) | Bill | 2 | 2026-02-13 | Done | 2026-02-14 | 2026-02-16 | 5 tools via registry. 16 tests (12 unit + 5 HTTP) passing
Test all tools: search, cart, orders, preferences |  | 2 | 2026-02-14 | Done | 2026-02-15 | 2026-02-15 | 5 tool types via tool registry
Frontend Integration & UI | Bill |  | 2026-02-13 | Done | 2026-02-17 | 2026-02-14 | WebSocket streaming with JSON message parsing
Connect React frontend to backend via WebSocket |  | 2 | 2026-02-13 | Done | 2026-02-14 | 2026-02-15 | ProductCard, ProductGrid, CartDrawer rendering. Fixed name mismatch
Validate ProductCard rendering from API payloads |  | 2 | 2026-02-14 | Done | 2026-02-15 | 2026-02-17 | Full flow working. Fixed product_name vs name property bug
End-to-end flow: search > view > cart > order | Both | 2 | 2026-02-15 | Done | 2026-02-16 | 2026-02-18 | Tailwind responsive. Theme store dark/light. Error handling
UI polish: loading, errors, reconnect, responsive |  | 2 | 2026-02-16 | Done | 2026-02-17 | 2026-02-17 | Error handling + mobile layout
Data Expansion & RAG Tuning | Both |  | 2026-02-16 | Done | 2026-02-20 | 2026-02-18 | 42 products, 6 merchants, 42 categories (fashion, electronics, home, outdoor, beauty)
Curate 40+ products across 4 categories | Bill | 3 | 2026-02-16 | Done | 2026-02-18 | 2026-02-19 | Embeddings cached to disk. Graceful fallback when OpenAI unreachable
Regenerate disk-cached embeddings; reload numpy VectorStore | Arjun | 2 | 2026-02-18 | Done | 2026-02-19 | 2026-02-20 | RRF tuned. Smart JSON truncation to prevent broken payloads
Tune RRF weights; validate search quality | Arjun | 2 | 2026-02-19 | Done | 2026-02-20 | 2026-02-20 | Test across all 5 intent types
Cloud Deployment (v1) | Arjun |  | 2026-02-20 | Modified | 2026-02-23 |  | Never used Milvus. numpy vector DB eliminated need for Pinecone
Swap Milvus for Pinecone; update vector_db.py |  | 2 | 2026-02-20 | Done | 2026-02-21 |  | Local deployment prioritized. Cloud deployment planned for next phase
Deploy FastAPI backend to Render |  | 2 | 2026-02-21 | Done | 2026-02-22 |  | Deferred alongside backend deployment
Deploy React frontend to Vercel | Bill | 2 | 2026-02-21 | Done | 2026-02-22 | 2026-02-23 | Comprehensive local testing done. MONITORING.md created
E2E smoke test on production URLs | Both | 2 | 2026-02-22 | Deferred | 2026-02-23 |  | CORS, WebSocket, latency checks
QA & Demo Preparation | Both |  | 2026-02-23 | Done | 2026-02-27 | 2026-02-24 | Demo scenarios in test_system.py + MONITORING.md guide
Script 3 demo scenarios |  | 2 | 2026-02-23 | Done | 2026-02-24 | 2026-02-25 | 3 stacked bugs found and fixed (WebSocket, guardrails, fallback)
Stress test: concurrency, edge cases, guardrails | Arjun | 2 | 2026-02-24 | Done | 2026-02-25 | 2026-02-26 | 7-slide midterm deck + 10-min presentation script created
Build progress presentation deck | Bill | 3 | 2026-02-24 | Done | 2026-02-26 | 2026-02-27 | Presentation rehearsed with speaker notes for all slides
Rehearse demo; assign speaking roles |  | 2 | 2026-02-26 | Done | 2026-02-27 | 2026-02-27 | Timed run-through
Prototype Freeze & Buffer | Both |  | 2026-02-27 | Done | 2026-02-28 | 2026-03-04 | WebSocket parsing, guardrails, fallback chain all resolved
Fix remaining bugs; freeze feature scope |  | 2 | 2026-02-27 | Done | 2026-02-28 | 2026-03-06 | Code pushed to GitHub. MONITORING.md + architecture docs delivered
Tag v1.0 release; update README & docs | Arjun | 1 | 2026-02-28 | Done | 2026-02-28 | 2026-02-28 | Git tag + changelog
Iteration & Feature Enhancement | Both |  | 2026-03-02 | Done | 2026-03-20 | 2026-03-20 | All 6 enhancement tasks completed. NLP + UI features enhanced
Add authentication (JWT tokens) | Arjun | 5 | 2026-03-02 | Done | 2026-03-06 | 2026-03-06 | JWT token auth implemented; Azure MSAL + Google OAuth configured
Implement persistent user profiles (PostgreSQL) | Bill | 7 | 2026-03-02 | Done | 2026-03-08 | 2026-03-08 | In-memory user profiles with Zustand persistence; PostgreSQL deferred
Add proactive product recommendations engine | Arjun | 7 | 2026-03-07 | Done | 2026-03-13 | 2026-03-13 | Preference-based recommendations via extracted user preferences
Implement order history & re-order functionality | Bill | 7 | 2026-03-09 | Done | 2026-03-15 | 2026-03-15 | Order tracking tool (track_order) + get_cart tool added to registry
Multi-turn conversation context improvements | Arjun | 5 | 2026-03-14 | Done | 2026-03-18 | 2026-03-18 | Memory service handles multi-turn; foundation for coreference + summarization
Add product image display & category navigation | Bill | 5 | 2026-03-16 | Done | 2026-03-20 | 2026-03-20 | ProductCard with images, 50+ brand URL mappings, category browse
Advanced NLP & UI Enhancement | Both |  | 2026-03-30 | Done | 2026-04-05 | 2026-04-05 | Enhanced coreference, preferences, memory summarization, re-ranking, auth, UI
Enhanced CoreferenceResolver with LLM-powered pronoun resolution | Arjun | 2 | 2026-03-30 | Done | 2026-03-31 | 2026-03-31 | Resolves "it", "that one", "the first one" → explicit product names/IDs
Built preference extraction from conversational text (brands, sizes, styles) | Bill | 2 | 2026-03-30 | Done | 2026-03-31 | 2026-03-31 | LLM extracts preferences; regex signal detection for efficiency; persists across session
Implemented LLM memory summarization for context window management | Arjun | 2 | 2026-03-31 | Done | 2026-04-01 | 2026-04-01 | Auto-summarizes older turns when token limit exceeded; keeps recent 5 + compressed summary
Added fallback keyword summarization + token counting (~4 chars/token) |  | 1 | 2026-04-01 | Done | 2026-04-01 | 2026-04-02 | Graceful degradation when LLM unavailable; truncates products >6000 chars
Implemented preference-aware search re-ranking on RRF results | Bill | 1 | 2026-04-01 | Done | 2026-04-02 | 2026-04-02 | Stable boosting: +2.0 brand, +1.0 price ceiling, +0.5 size, +0.5 style (never demotes)
Fixed multi-source API priority ordering (SerpAPI > RapidAPI > eBay > local) | Arjun | 1 | 2026-04-02 | Done | 2026-04-02 | 2026-04-03 | Resolved bug where fallback APIs called before primary; proper cascading now
Implemented Login/Auth page with OAuth (Azure MSAL + Google) | Arjun | 2 | 2026-04-03 | Done | 2026-04-04 | 2026-04-04 | 176 lines; guest mode badge; JWT session tokens; branded login UI
Added all backend button functionality + new logo & branding | Bill | 1 | 2026-04-03 | Done | 2026-04-04 | 2026-04-04 | Cart add/remove/update, saved items, checkout buttons wired; new gradient logo
Integration testing & validation of all NLP + UI enhancements | Both | 1 | 2026-04-04 | Done | 2026-04-05 | 2026-04-05 | Tested coreference in multi-turn, preference persistence, memory summarization, full regression
Testing & User Feedback | Both |  | 2026-03-21 | Done | 2026-04-05 | 2026-04-05 | Test suite + user testing + feedback analysis + fixes all completed
Write comprehensive test suite (unit + integration) | Arjun | 7 | 2026-03-21 | Done | 2026-03-27 | 2026-03-27 | Achieved 80%+ coverage; 16 tests (12 unit + 5 HTTP) passing
Conduct user testing (5-8 participants) |  | 8 | 2026-03-23 | Done | 2026-03-30 | 2026-03-30 | 6 participants tested; sessions recorded; key feedback documented
Analyze feedback; prioritize improvements |  | 4 | 2026-03-30 | Done | 2026-04-02 | 2026-04-02 | Ranked backlog created; top issues: coreference, search personalization, button gaps
Implement high-priority feedback changes |  | 4 | 2026-04-02 | Done | 2026-04-05 | 2026-04-05 | Top 5 issues fixed: coreference, preference re-ranking, memory, buttons, auth
Final Optimization & Documentation | Both |  | 2026-04-06 | Done | 2026-04-19 | 2026-04-18 | All optimization, security, docs, deploy, and regression work completed
Performance optimization (caching, lazy loading) | Arjun | 5 | 2026-04-06 | Done | 2026-04-10 | 2026-04-10 | Embedding disk cache, lazy WS reconnect, markdown-to-jsx memoized; latency benchmarks logged
Security audit (CORS, rate limiting, validation) |  | 5 | 2026-04-08 | Done | 2026-04-12 | 2026-04-18 | JWT HS256 pinning + exp/sub/jti/iat, token denylist, /auth/guest rate limit, CSP headers, audit log, schema validators (test_phase1_security.py, 15 checks passing)
Write technical documentation & architecture guide | Arjun | 6 | 2026-04-10 | Done | 2026-04-15 | 2026-04-15 | MONITORING.md architecture flow + file map; README architecture section; crash_test_results.md
Write user guide & demo walkthrough | Bill | 6 | 2026-04-10 | Done | 2026-04-15 | 2026-04-15 | START_HERE.md quickstart + example queries; demo walkthrough checklist
Deploy final production version (v2.0) |  | 3 | 2026-04-15 | Done | 2026-04-17 | 2026-04-17 | v2.0 tagged; frontend and backend deployed with hardened auth and CORS locked to FRONTEND_URL
Final regression test on production |  | 3 | 2026-04-17 | Done | 2026-04-19 | 2026-04-18 | Full regression run on prod: auth, cart merge, WS resiliency, category routing, Stripe sandbox checkout all passing
Final Presentation & Submission | Both |  | 2026-04-20 | In Progress | 2026-05-01 |  | Deck build underway; delivery scheduled 2026-04-28, submission 2026-05-01
Build final presentation deck (DS 440 rubric) | Bill | 5 | 2026-04-20 | In Progress | 2026-04-24 |  | Deck drafted using Results_Conclusions_Future_Work.docx as backbone
Prepare live demo environment & backup recording | Arjun | 4 | 2026-04-22 |  | 2026-04-25 |  | Screen recording as fallback
Full dress rehearsal (timed, with Q&A prep) |  | 3 | 2026-04-25 |  | 2026-04-27 |  | 25 min max + 5 min Q&A
Final presentation delivery to class |  | 1 | 2026-04-28 |  | 2026-04-28 |  | Live demo + slides
Submit all deliverables (code, docs, deck, report) | Arjun | 4 | 2026-04-28 |  | 2026-05-01 |  | Canvas submission